## Bug Status
Defect Status
Defect Status | Immediate | Urgent | High | Normal | Low | Total
Closed | 0 | 1 | 27 | 63 | 1 | 92
New | 0 | 0 | 0 | 1 | 0 | 1
Backlog | 0 | 0 | 4 | 15 | 0 | 19
Done | 0 | 0 | 1 | 3 | 0 | 4
Fixed | 0 | 0 | 1 | 1 | 0 | 2
In Progress | 0 | 0 | 1 | 0 | 0 | 1
Total | 0 | 1 | 34 | 83 | 1 | 119
Assigned User
User | Closed | New | Backlog | Done | Fixed | In Progress |  |  | Total
Ashish Bastakoti | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40
Subin Shakya | 2 | 1 | 7 | 0 | 0 | 1 | 0 | 0 | 11
Saman Kapali | 17 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 20
Harris Gurung | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 3
Sapna Tuladhar | 29 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 30
samjhana kc | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 9
Chris Lurty | 2 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 5
Lalit Thapa | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Total | 92 | 1 | 19 | 4 | 2 | 1 | 0 | 0 | 119

## Task Status
Assigned User
User | Backlog | Closed | Done | Fixed | In Progress |  |  |  | Total
Subin Shakya | 6 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 7
Ashish Bastakoti | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Saman Kapali | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 3
N/A | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Chris Lurty | 4 | 5 | 15 | 0 | 5 | 0 | 0 | 0 | 29
samjhana kc | 13 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 15
Lalit Thapa | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Jeetendra Maharjan | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
0
Total | 26 | 7 | 16 | 1 | 8 | 0 | 0 | 0 | 58

## Bug
Row no. | # | Tracker | Status | Priority | Subject | Assignee | Updated | Assignee | Status
2 | 6706 | Bug | Closed | Normal | The border color of the search box was supposed to be the primary store color. | Ashish Bastakoti | 2017-05-26 12:31 | Ashish Bastakoti | Closed | Tracker Type
3 | 6705 | Bug | Closed | High | The logo position on the Front-end for the product image must be exact per image. | Ashish Bastakoti | 2017-05-25 17:12 | Subin Shakya | New | Bug
5 | 6671 | Bug | Closed | Normal | The additional text are displayed as cut off in the text field in the mozilla browser | Ashish Bastakoti | 2017-05-25 14:34 | Saman Kapali | Backlog
6 | 6668 | Bug | Closed | Normal | There are only two logos available for the product yet, customer is able to choose any logo of the store for that product via cart checkout page | Ashish Bastakoti | 2017-05-25 14:15 | Harris Gurung | Done
7 | 6665 | Bug | New | Normal | Issue while deleting a logo. | Subin Shakya | 2017-05-26 09:23 | Sapna Tuladhar | Fixed
8 | 6664 | Bug | Closed | Normal | The additional text display is not displayed in the orders confirmation page | Ashish Bastakoti | 2017-05-22 17:28 | samjhana kc | In Progress
10 | 6642 | Bug | Closed | Normal | The overlay doesn't cover the search on the Store pages. | Ashish Bastakoti | 2017-05-25 14:33 | Chris Lurty
11 | 6639 | Bug | Closed | High | The custom Products added to the store from the Store Appearances is not displayed on that Store Homepage on Front-end. | Ashish Bastakoti | 2017-05-22 17:03 | Lalit Thapa
12 | 6635 | Bug | Closed | High | PDO exception Error | Ashish Bastakoti | 2017-05-25 13:51
13 | 6603 | Bug | Backlog | High | Issues during custom order creation | Subin Shakya | 2017-05-26 09:24
14 | 6591 | Bug | Closed | High | Browser specific bug during order creation. | Subin Shakya | 2017-05-16 17:34
15 | 6565 | Bug | Done | Normal | Subcategories not saved. | Saman Kapali | 2017-05-12 15:41
16 | 6556 | Bug | Done | Normal | Price does not change with change of Logo | Saman Kapali | 2017-05-12 15:53
17 | 6546 | Bug | Closed | High | The Custom Products created from backend when clicked display "Page Not Found" | Ashish Bastakoti | 2017-05-15 10:41
18 | 6537 | Bug | Closed | Normal | Search Issues in Front-end | Ashish Bastakoti | 2017-05-11 16:17
20 | 6527 | Bug | Closed | Normal | Missing Image breaks logo display | Harris Gurung | 2017-05-04 22:12
21 | 6526 | Bug | Backlog | Normal | The color scroll on Product Search page for the thumbnail displays color on next scroll even though there is space on the same section | Harris Gurung | 2017-05-04 16:50
22 | 6525 | Bug | Backlog | Normal | Issue regarding No Images and Logo | Saman Kapali | 2017-05-22 17:00
23 | 6507 | Bug | Closed | Normal | If filter of price/feature is applied store-wide, then in some cases, a single color option is available in product listing page. | Ashish Bastakoti | 2017-05-22 16:46
24 | 6494 | Bug | Closed | Normal | Price roundup mismatch | Ashish Bastakoti | 2017-05-22 16:59
25 | 6483 | Bug | Closed | Normal | Issues related with product listings format. | Sapna Tuladhar | 2017-05-15 10:42
26 | 6482 | Bug | Backlog | Normal | The shipping rates are provided 0 | Harris Gurung | 2017-05-02 12:44
27 | 6480 | Bug | Backlog | Normal | While viewing order details from backend. | Subin Shakya | 2017-05-26 09:30
30 | 6474 | Bug | Closed | Normal | Issues regarding price of length | Saman Kapali | 2017-05-08 16:06
31 | 6457 | Bug | Closed | Normal | Product with no size available couldn't be added to the create new order page. | Ashish Bastakoti | 2017-05-10 10:19
33 | 6454 | Bug | Closed | Normal | Issues related with creating new order. | Subin Shakya | 2017-05-10 10:34
34 | 6436 | Bug | Closed | Normal | If the Coupon is applied but the order is not made and User adds more products to cart then, the previous coupon value is still displayed on the Cart Page | Ashish Bastakoti | 2017-04-21 12:48
35 | 6435 | Bug | Closed | Normal | The Coupon Calculation for Item Coupon type is not correct | Ashish Bastakoti | 2017-04-21 17:58
36 | 6421 | Bug | Backlog | High | The Order for the nametags if clicked display "Page Not Found" | Subin Shakya | 2017-04-18 16:13
37 | 6420 | Bug | Backlog | High | The application crashed when browser's back button was clicked from product detail page which was visited after the filters were used | samjhana kc | 2017-04-18 15:58
38 | 6409 | Bug | Backlog | Normal | New item couldn't be added on edit order edit page. | Subin Shakya | 2017-04-17 17:56
39 | 6394 | Bug | Closed | Normal | Order details pages have been crashing. | Sapna Tuladhar | 2017-05-15 10:42
40 | 6393 | Bug | Fixed | Normal | Incorrect warning message is appearing for the coupon value fied. | Sapna Tuladhar | 2017-05-02 16:10
41 | 6344 | Bug | Closed | Normal | Unable to view order details. | Sapna Tuladhar | 2017-05-15 10:43
42 | 6288 | Bug | Backlog | Normal | Logo can be added without uploading logo image file. | Subin Shakya | 2017-03-28 10:13
43 | 6285 | Bug | Backlog | Normal | Calculation error found on the product detail page(after adding logo from the back end). | samjhana kc | 2017-03-27 15:43
44 | 6278 | Bug | Closed | Normal | The edited item lines/delete actions aren't saved in Order Details | Ashish Bastakoti | 2017-05-02 10:46
45 | 6274 | Bug | Backlog | Normal | On clicking menu, headings are overlapping. | samjhana kc | 2017-03-22 14:57
46 | 6264 | Bug | Closed | Normal | Shipping address replication. | Sapna Tuladhar | 2017-03-23 13:39
47 | 6263 | Bug | Backlog | Normal | calculation error found on the order history page. | samjhana kc | 2017-03-22 16:16
48 | 6262 | Bug | Backlog | Normal | Keep inventory up to date. | samjhana kc | 2017-03-21 11:24
49 | 6241 | Bug | Closed | Normal | When using search feature to find products. | Sapna Tuladhar | 2017-05-15 10:43
50 | 6223 | Bug | Closed | Normal | Logo couldn't be deleted as this logo has already been assigned to the product(placed order). | Sapna Tuladhar | 2017-03-20 13:00
51 | 6219 | Bug | Closed | High | Product detail page Crash Scenario | Sapna Tuladhar | 2017-03-21 11:43
52 | 6218 | Bug | Closed | Normal | Validation is required in Logo file upload. | Ashish Bastakoti | 2017-03-20 09:56
53 | 6208 | Bug | Closed | High | The product quantity and price issue in the Cart page | Ashish Bastakoti | 2017-03-20 10:27
54 | 6207 | Bug | Closed | Normal | Some product's detail pages have been crashing. | Sapna Tuladhar | 2017-03-21 13:05
55 | 6206 | Bug | Closed | Normal | The correct number of products cannot be ordered from a grid view | Ashish Bastakoti | 2017-03-20 10:26
56 | 6204 | Bug | Closed | Normal | Prices can be in decimal form. | Sapna Tuladhar | 2017-03-20 12:52
57 | 6203 | Bug | Closed | Normal | If user tries to edit split order, error page is thrown. | Sapna Tuladhar | 2017-03-20 11:47
58 | 6199 | Bug | Fixed | High | Stores Module (Front-end "Shipping Page") : JS issue | Chris Lurty | 2017-03-21 11:03
59 | 6198 | Bug | Closed | High | Stores Module (Front-end "Product Detail Page") : the logos on modal image problem | Ashish Bastakoti | 2017-03-21 11:10
60 | 6196 | Bug | Closed | High | looks like the S3 permissions aren't set correctly | Ashish Bastakoti | 2017-03-20 10:26
61 | 6195 | Bug | Closed | High | Store Module (Back-end) : Admin cannot edit/delete logo in Logo tab from Store Edit | Ashish Bastakoti | 2017-03-20 09:48
62 | 6181 | Bug | Closed | High | Crash during order placement when no business address supplied | Saman Kapali | 2017-03-15 16:10
63 | 6178 | Bug | Closed | High | If the Order detail for a customer is edited, all the other details are also replaced | Ashish Bastakoti | 2017-03-23 12:41
64 | 6177 | Bug | Closed | High | The Customer and Shipping Info if changed, shouldn't be updated to the Login Information and default Shipping info for Customer | Ashish Bastakoti | 2017-03-23 12:41
65 | 6174 | Bug | Closed | Normal | If the admin privileges is switched On/Off, the contact number is deleted from the customer info | Ashish Bastakoti | 2017-03-20 09:28
66 | 6173 | Bug | Closed | Low | Button enabling issue in contact info | Saman Kapali | 2017-03-23 09:35
67 | 6170 | Bug | Closed | Normal | User can add products to cart more than that mentioned in stock | Ashish Bastakoti | 2017-03-21 11:26
68 | 6169 | Bug | Closed | Normal | For the stores with no default products but custom products, the product doesn't display if selected from menu but the products display randomly | Ashish Bastakoti | 2017-03-21 11:05
70 | 6162 | Bug | Backlog | High | If a certain product of specific size from a bulk is changed status in vendor-orders then the main orders are not displayed in any status's page. | Subin Shakya | 2017-03-14 16:52
71 | 6161 | Bug | Closed | Normal | Provide Validation to Customer Info and Shipping Info in Order Details page as well. | Ashish Bastakoti | 2017-03-23 12:33
72 | 6160 | Bug | Closed | Normal | Prices are left aligned on thumbnails of default products. | Sapna Tuladhar | 2017-03-16 09:39
73 | 6159 | Bug | Closed | Normal | The total price on the data table for Orders should be Net-Total, not sub-total | Ashish Bastakoti | 2017-03-20 09:27
74 | 6157 | Bug | Closed | Normal | Product quantity doesn't match with the total number of selected products on default_products page. | Sapna Tuladhar | 2017-03-20 12:59
75 | 6155 | Bug | Closed | High | If a company is created without any stores, and the company URL is accessed, the application crashes. | Ashish Bastakoti | 2017-03-21 11:09
76 | 6154 | Bug | Closed | Normal | Edit feature is not working for shipping address. | Sapna Tuladhar | 2017-03-16 11:39
77 | 6153 | Bug | Closed | Normal | Error while spliting order | Saman Kapali | 2017-03-15 13:39
78 | 6152 | Bug | Closed | Normal | While adding new address into shipping option section. | Sapna Tuladhar | 2017-03-21 13:43
79 | 6151 | Bug | Closed | Normal | Price and size match issue, while editing order. | Saman Kapali | 2017-03-15 16:50
80 | 6150 | Bug | Closed | Normal | Existing products are not displayed in default products section but is displayed on all products section in Stores module | Ashish Bastakoti | 2017-03-20 09:25
81 | 6139 | Bug | Closed | Normal | On clicking Replace button from Vendor-Order, Order Status is blanked and no orders displayed in Order Status's page. | Ashish Bastakoti | 2017-03-20 09:27
82 | 6136 | Bug | Closed | Normal | On clicking dkpk store, page crashes. | Sapna Tuladhar | 2017-03-16 10:19
83 | 6135 | Bug | Closed | Normal | Exception should be handled properly if user tries to open invalid url from back end. | Sapna Tuladhar | 2017-03-20 10:21
84 | 6130 | Bug | Closed | Normal | Products remain on cart after a order is placed successfully | Saman Kapali | 2017-03-15 16:51
85 | 6129 | Bug | Backlog | Normal | Provide Admin privileges to user and refresh the front end, doesnot display Logged In as Admin | samjhana kc | 2017-03-13 14:47
86 | 6128 | Bug | In Progress | High | The price do not match in Order Processing (BackEnd) | Subin Shakya | 2017-03-16 12:38
87 | 6127 | Bug | Closed | Normal | "Allow Shipping to Other Addresses" toggle switch couldn't be disabled. | Sapna Tuladhar | 2017-03-16 11:17
88 | 6126 | Bug | Backlog | Normal | The twilo validation is not working if the phone number is added from the back-end which was not validated properly there too. | samjhana kc | 2017-03-13 13:49
89 | 6125 | Bug | Closed | Normal | When trying to add new store from view company section. | Sapna Tuladhar | 2017-03-16 11:16
90 | 6124 | Bug | Closed | Normal | Though the Store is created from Company Edit, an error message is provided! | Ashish Bastakoti | 2017-03-20 09:25
91 | 6123 | Bug | Closed | Normal | Exception should be handled properly if user tried to place order twice. | Sapna Tuladhar | 2017-03-16 11:13
92 | 6120 | Bug | Closed | High | Crash during order placement | Saman Kapali | 2017-03-15 16:47
93 | 6119 | Bug | Closed | Normal | Price unit is only available for default items. | Sapna Tuladhar | 2017-03-16 11:11
94 | 6118 | Bug | Closed | Normal | Both the stores are considered default store and non of them can be deleted | Ashish Bastakoti | 2017-03-13 11:11
95 | 6117 | Bug | Closed | Normal | style id without having preview image is displaying on the drop down list when tried to add default items. | Sapna Tuladhar | 2017-03-16 11:01
96 | 6115 | Bug | Closed | Normal | Allow shipping to other addresses toggle switch should be auto active. | Sapna Tuladhar | 2017-03-16 10:50
97 | 6113 | Bug | Backlog | Normal | Shipping Info Page is not displayed instead a message is provided after valid details are entered from Contact Info Page | samjhana kc | 2017-03-10 14:39
98 | 6112 | Bug | Closed | Normal | Unable to delete a carted item on windows. | Sapna Tuladhar | 2017-03-20 10:19
99 | 6111 | Bug | Closed | Normal | Exception is thrown when tried to enter duplicate email address in customer page. | Sapna Tuladhar | 2017-03-14 15:54
100 | 6110 | Bug | Closed | Normal | The admin privileges if turned off cannot be switched on again | Ashish Bastakoti | 2017-03-13 11:35
101 | 6108 | Bug | Closed | High | Error while adding products | Saman Kapali | 2017-03-10 16:09
102 | 6105 | Bug | Backlog | Normal | Use same validation through out the application, the submit button is disabled even if required fields are entered. | Subin Shakya | 2017-03-20 10:18
103 | 6104 | Bug | Closed | Normal | hierarchy during adding categories | Lalit Thapa | 2017-03-10 16:08
106 | 6100 | Bug | Closed | High | Cannot add two products with same name in same custom category and | Saman Kapali | 2017-03-10 16:48
107 | 6099 | Bug | Closed | Normal | When clicked on eye icon to view the image of carted item. | Sapna Tuladhar | 2017-03-16 10:43
108 | 6098 | Bug | Closed | High | Can edit billing without edit permission | Saman Kapali | 2017-03-14 09:10
109 | 6097 | Bug | Closed | Normal | When using search feature to find company/store. | Sapna Tuladhar | 2017-03-16 10:30
110 | 6095 | Bug | Closed | Normal | The buttons should be disabled in view mode | Ashish Bastakoti | 2017-03-13 11:21
111 | 6092 | Bug | Closed | High | The UI and js not working in Safari browser | Ashish Bastakoti | 2017-03-21 09:25
112 | 6091 | Bug | Closed | Normal | After the admin is created for a store the user is directed back to the Store edit mode but the admin is not listed! | Ashish Bastakoti | 2017-03-13 11:06
113 | 6090 | Bug | Closed | Normal | Stores - Stores (Create Company) : The detail tab should open by default | Ashish Bastakoti | 2017-03-13 11:32
114 | 6088 | Bug | Closed | Normal | Display a default message in every data table if there are no items | Ashish Bastakoti | 2017-03-20 09:24
115 | 6084 | Bug | Backlog | Normal | Slider is not working on front end. | samjhana kc | 2017-03-16 10:13
116 | 6080 | Bug | Closed | High | Error after a product is deleted from the order list. | Saman Kapali | 2017-03-10 14:45
117 | 6078 | Bug | Closed | High | Browser Specific bug | Saman Kapali | 2017-03-10 14:40
118 | 6077 | Bug | Closed | High | Zero total error | Saman Kapali | 2017-03-10 14:39
119 | 6076 | Bug | Closed | High | Page crash while order with amount greater than $999 | Saman Kapali | 2017-03-10 17:31
120 | 6072 | Bug | Closed | Normal | When moving cursor towards sign out option. | Sapna Tuladhar | 2017-03-13 15:01
121 | 6071 | Bug | Closed | Normal | When edited the item size, price of the item got resetted. | Sapna Tuladhar | 2017-03-13 15:01
122 | 6069 | Bug | Closed | Normal | When clicked on order now button, eception is thrown. | Sapna Tuladhar | 2017-03-16 09:42
124 | 6061 | Bug | Closed | High | Crash during order placement | Saman Kapali | 2017-03-10 14:46
125 | 6060 | Bug | Closed | High | User deletion not handled properly. | Saman Kapali | 2017-03-10 15:43
138 | 5986 | Bug | Done | High | The store products aren't updating | Chris Lurty | 2017-02-22 11:33
149 | 5973 | Bug | Done | Normal | The footer should have a minimum height so that it is always in the foot of the page. | Chris Lurty | 2017-02-21 18:03
166 | 5597 | Bug | Closed | High | Admin login validation | Saman Kapali | 2016-12-30 13:02
172 | 5307 | Bug | Closed | Urgent | Product Import Error | Chris Lurty | 2016-11-10 21:06
193 | 5160 | Bug | Closed | High | Error when accessing product page | Chris Lurty | 2016-11-07 21:37
Formulas:
Updated = IF([Row no.]="","",INDIRECT("Raw!G"&[Row no.]))

## Task
Row no. | # | Tracker | Status | Priority | Subject | Assignee | Updated | Assignee | Status
9 | 6652 | Task | Backlog | Normal | Change the Fedex suggested address to dropdown in address validation | Subin Shakya | 2017-05-22 11:52 | Subin Shakya | Backlog | Tracker Type
19 | 6532 | Task | Closed | Normal | Default Logo | Ashish Bastakoti | 2017-05-22 17:02 | Ashish Bastakoti | Closed | Task
28 | 6479 | Task | Done | Normal | Display issues with cart, when length is included | Saman Kapali | 2017-05-12 15:53 | Saman Kapali | Done
69 | 6168 | Task | Backlog | Normal | Updated Home Page | N/A | 2017-03-16 09:15 | N/A | Fixed
123 | 6063 | Task | Closed | Normal | Admin order creating issue | Saman Kapali | 2017-03-14 09:10 | Chris Lurty | In Progress
126 | 6051 | Task | Done | Normal | Changes in User - Backend (User Module) | Chris Lurty | 2017-03-13 11:40 | samjhana kc
127 | 6050 | Task | Done | Normal | Changes in Details tab - Backend (Store Module) | Chris Lurty | 2017-03-13 11:40 | Lalit Thapa
128 | 6049 | Task | Backlog | Normal | Changes in Company - Frontend (Stores Module) | samjhana kc | 2017-03-08 09:20 | Jeetendra Maharjan
129 | 6048 | Task | Done | Normal | Changes in Company - Backend (Stores Module) | Chris Lurty | 2017-03-13 11:40
130 | 6039 | Task | Fixed | High | Id assignment of webelements. | Saman Kapali | 2017-03-07 15:54
132 | 6005 | Task | Backlog | Normal | Store HomePage - Frontend (Store Module) | samjhana kc | 2017-02-28 00:24
133 | 6003 | Task | Done | Normal | Changes in Products tab - Backend (Stores Modules) | Chris Lurty | 2017-02-27 15:48
134 | 6002 | Task | Backlog | Normal | Add Custom Filters in the Frontend | samjhana kc | 2017-02-27 13:13
135 | 6001 | Task | In Progress | Normal | Changes in Appearance - Backend (Stores Modules) | Subin Shakya | 2017-03-10 14:43
136 | 6000 | Task | Backlog | Normal | Changes in Shipping Option - Backend (Stores Module) | samjhana kc | 2017-03-10 14:56
137 | 5999 | Task | Backlog | Normal | Changes to the Billing System - Backend (Stores Module) | Subin Shakya | 2017-02-28 13:18
140 | 5982 | Task | Backlog | Normal | Messaging - Again | Lalit Thapa | 2017-02-21 02:47
141 | 5981 | Task | Backlog | Normal | Handle the Pricing in both back-end and Front-end using floats | Subin Shakya | 2017-02-20 16:39
151 | 5925 | Task | Backlog | Normal | Cart Page Update | samjhana kc | 2017-02-07 03:07
152 | 5907 | Task | Backlog | Normal | Order Confirmation Email | samjhana kc | 2017-02-03 00:26
153 | 5848 | Task | Done | Normal | Quick Fixes - Please fix ASAP! | Chris Lurty | 2017-02-22 10:49
154 | 5847 | Task | Backlog | Normal | Shipping | samjhana kc | 2017-01-26 00:45
155 | 5846 | Task | Backlog | Normal | Credit Card Processing | samjhana kc | 2017-01-24 21:58
156 | 5770 | Task | Done | Normal | Company page and Store page in Frontend | Chris Lurty | 2017-03-20 13:28
157 | 5767 | Task | Backlog | Normal | Please explain the use of cookies and Company Store addresses during checkout. | Chris Lurty | 2017-01-27 00:50
158 | 5766 | Task | Backlog | Normal | Please define the role of a Store Admin | Subin Shakya | 2017-01-12 20:38
159 | 5765 | Task | Backlog | Normal | Please explain 'Product Ordering Page' | Subin Shakya | 2017-02-03 00:10
160 | 5760 | Task | Done | High | Please specify the Product Import Method for Vendor Barco Uniforms and provide the details. | Chris Lurty | 2017-02-16 10:21
161 | 5759 | Task | Done | Normal | Please specify the Product Import Method for Vendor White Swan and provide the details. | Chris Lurty | 2017-02-10 09:30
162 | 5758 | Task | Done | Normal | Please specify the Product Import Method for Vendor Landau and provide the details. | Chris Lurty | 2017-02-07 10:56
163 | 5757 | Task | Done | Normal | Please specify the Product Import Method for Vendor Strategic Partners and provide the details. | Chris Lurty | 2017-02-07 10:56
164 | 5756 | Task | Done | Normal | Please specify the Product Import Method for Vendor AlphaBorder and provide the details. | Chris Lurty | 2017-02-07 10:55
165 | 5755 | Task | Done | Normal | Please specify the Product Import Method for Vendor SanMar and provide the details. | Chris Lurty | 2017-02-07 10:55
167 | 5595 | Task | Backlog | Normal | Footer | samjhana kc | 2016-12-30 10:25
168 | 5510 | Task | Backlog | Normal | Inventory | Chris Lurty | 2016-12-30 16:57
169 | 5502 | Task | Backlog | Normal | title, url and search | samjhana kc | 2016-12-13 17:09
170 | 5343 | Task | In Progress | Normal | Users Section | Chris Lurty | 2016-11-28 16:06
171 | 5311 | Task | Closed | Urgent | Git File List | Chris Lurty | 2016-12-05 20:53
173 | 5292 | Task | Backlog | High | Store Logos | Subin Shakya | 2017-01-04 23:04
174 | 5291 | Task | Backlog | High | Product Pricing | samjhana kc | 2017-01-16 21:56
175 | 5290 | Task | Backlog | High | Database Access | Chris Lurty | 2016-11-14 12:15
176 | 5281 | Task | Backlog | Normal | Checkout Page | Jeetendra Maharjan | 2016-11-18 21:22
177 | 5263 | Task | In Progress | Normal | Shopping Cart | samjhana kc | 2016-11-09 03:44
178 | 5246 | Task | Backlog | Normal | Icons | samjhana kc | 2016-11-08 10:48
179 | 5236 | Task | Done | Normal | Store Logos | Chris Lurty | 2017-03-20 09:53
180 | 5235 | Task | Done | Normal | Companies | Chris Lurty | 2017-02-07 10:57
181 | 5234 | Task | In Progress | Normal | Updated Product Search Page | Chris Lurty | 2017-01-17 09:01
182 | 5233 | Task | In Progress | Normal | Use subdomains for assets | samjhana kc | 2016-11-15 00:24
183 | 5213 | Task | In Progress | Normal | Store Appearance | Chris Lurty | 2016-11-16 17:31
184 | 5212 | Task | In Progress | Normal | Product Detail Page | Chris Lurty | 2017-01-13 08:59
185 | 5195 | Task | Backlog | Normal | css and js file organization | samjhana kc | 2016-12-30 07:06
186 | 5180 | Task | Done | Urgent | Store Product List | Chris Lurty | 2017-02-07 17:32
187 | 5179 | Task | In Progress | Normal | Default Products Section | Chris Lurty | 2016-11-14 12:25
189 | 5164 | Task | Closed | Normal | Store form match format | Chris Lurty | 2016-11-07 21:32
190 | 5163 | Task | Closed | Low | switches missing in the store form | Chris Lurty | 2016-11-07 21:39
191 | 5162 | Task | Closed | Low | Reduce size of checkboxes and switches | Chris Lurty | 2016-11-07 21:36
192 | 5161 | Task | Closed | Low | Strategic Partners Import | Chris Lurty | 2016-11-08 00:56
197 | 5142 | Task | Backlog | High | Regarding Campaign | Chris Lurty | 2016-10-25 21:22
Formulas:
Updated = IF([Row no.]="","",INDIRECT("Raw!G"&[Row no.]))

## Raw
# | Tracker | Status | Priority | Subject | Assignee | Updated | Tracker Type
6706 | Bug | Closed | Normal | The border color of the search box was supposed to be the primary store color. | Ashish Bastakoti | 2017-05-26 12:31 | Closed
6705 | Bug | Closed | High | The logo position on the Front-end for the product image must be exact per image. | Ashish Bastakoti | 2017-05-25 17:12 | Backlog
6704 | Feature | Backlog | Normal | "Forgot Password" functionality in the front-end Sign In Module must be operational | Lalit Thapa | 2017-05-25 22:45 | New
6671 | Bug | Closed | Normal | The additional text are displayed as cut off in the text field in the mozilla browser | Ashish Bastakoti | 2017-05-25 14:34 | Done
6668 | Bug | Closed | Normal | There are only two logos available for the product yet, customer is able to choose any logo of the store for that product via cart checkout page | Ashish Bastakoti | 2017-05-25 14:15 | Fixed
6665 | Bug | New | Normal | Issue while deleting a logo. | Subin Shakya | 2017-05-26 09:23 | In Progress
6664 | Bug | Closed | Normal | The additional text display is not displayed in the orders confirmation page | Ashish Bastakoti | 2017-05-22 17:28
6652 | Task | Backlog | Normal | Change the Fedex suggested address to dropdown in address validation | Subin Shakya | 2017-05-22 11:52
6642 | Bug | Closed | Normal | The overlay doesn't cover the search on the Store pages. | Ashish Bastakoti | 2017-05-25 14:33
6639 | Bug | Closed | High | The custom Products added to the store from the Store Appearances is not displayed on that Store Homepage on Front-end. | Ashish Bastakoti | 2017-05-22 17:03
6635 | Bug | Closed | High | PDO exception Error | Ashish Bastakoti | 2017-05-25 13:51
6603 | Bug | Backlog | High | Issues during custom order creation | Subin Shakya | 2017-05-26 09:24
6591 | Bug | Closed | High | Browser specific bug during order creation. | Subin Shakya | 2017-05-16 17:34
6565 | Bug | Done | Normal | Subcategories not saved. | Saman Kapali | 2017-05-12 15:41
6556 | Bug | Done | Normal | Price does not change with change of Logo | Saman Kapali | 2017-05-12 15:53
6546 | Bug | Closed | High | The Custom Products created from backend when clicked display "Page Not Found" | Ashish Bastakoti | 2017-05-15 10:41
6537 | Bug | Closed | Normal | Search Issues in Front-end | Ashish Bastakoti | 2017-05-11 16:17
6532 | Task | Closed | Normal | Default Logo | Ashish Bastakoti | 2017-05-22 17:02
6527 | Bug | Closed | Normal | Missing Image breaks logo display | Harris Gurung | 2017-05-04 22:12
6526 | Bug | Backlog | Normal | The color scroll on Product Search page for the thumbnail displays color on next scroll even though there is space on the same section | Harris Gurung | 2017-05-04 16:50
6525 | Bug | Backlog | Normal | Issue regarding No Images and Logo | Saman Kapali | 2017-05-22 17:00
6507 | Bug | Closed | Normal | If filter of price/feature is applied store-wide, then in some cases, a single color option is available in product listing page. | Ashish Bastakoti | 2017-05-22 16:46
6494 | Bug | Closed | Normal | Price roundup mismatch | Ashish Bastakoti | 2017-05-22 16:59
6483 | Bug | Closed | Normal | Issues related with product listings format. | Sapna Tuladhar | 2017-05-15 10:42
6482 | Bug | Backlog | Normal | The shipping rates are provided 0 | Harris Gurung | 2017-05-02 12:44
6480 | Bug | Backlog | Normal | While viewing order details from backend. | Subin Shakya | 2017-05-26 09:30
6479 | Task | Done | Normal | Display issues with cart, when length is included | Saman Kapali | 2017-05-12 15:53
6477 | Backlog | Closed | Normal | Limitation with the Current Flow of the System | Ashish Bastakoti | 2017-05-22 14:10
6474 | Bug | Closed | Normal | Issues regarding price of length | Saman Kapali | 2017-05-08 16:06
6457 | Bug | Closed | Normal | Product with no size available couldn't be added to the create new order page. | Ashish Bastakoti | 2017-05-10 10:19
6455 | Backlog | Closed | Normal | When splitted order including paid amount, paid amount get vanished. | Ashish Bastakoti | 2017-05-11 11:43
6454 | Bug | Closed | Normal | Issues related with creating new order. | Subin Shakya | 2017-05-10 10:34
6436 | Bug | Closed | Normal | If the Coupon is applied but the order is not made and User adds more products to cart then, the previous coupon value is still displayed on the Cart Page | Ashish Bastakoti | 2017-04-21 12:48
6435 | Bug | Closed | Normal | The Coupon Calculation for Item Coupon type is not correct | Ashish Bastakoti | 2017-04-21 17:58
6421 | Bug | Backlog | High | The Order for the nametags if clicked display "Page Not Found" | Subin Shakya | 2017-04-18 16:13
6420 | Bug | Backlog | High | The application crashed when browser's back button was clicked from product detail page which was visited after the filters were used | samjhana kc | 2017-04-18 15:58
6409 | Bug | Backlog | Normal | New item couldn't be added on edit order edit page. | Subin Shakya | 2017-04-17 17:56
6394 | Bug | Closed | Normal | Order details pages have been crashing. | Sapna Tuladhar | 2017-05-15 10:42
6393 | Bug | Fixed | Normal | Incorrect warning message is appearing for the coupon value fied. | Sapna Tuladhar | 2017-05-02 16:10
6344 | Bug | Closed | Normal | Unable to view order details. | Sapna Tuladhar | 2017-05-15 10:43
6288 | Bug | Backlog | Normal | Logo can be added without uploading logo image file. | Subin Shakya | 2017-03-28 10:13
6285 | Bug | Backlog | Normal | Calculation error found on the product detail page(after adding logo from the back end). | samjhana kc | 2017-03-27 15:43
6278 | Bug | Closed | Normal | The edited item lines/delete actions aren't saved in Order Details | Ashish Bastakoti | 2017-05-02 10:46
6274 | Bug | Backlog | Normal | On clicking menu, headings are overlapping. | samjhana kc | 2017-03-22 14:57
6264 | Bug | Closed | Normal | Shipping address replication. | Sapna Tuladhar | 2017-03-23 13:39
6263 | Bug | Backlog | Normal | calculation error found on the order history page. | samjhana kc | 2017-03-22 16:16
6262 | Bug | Backlog | Normal | Keep inventory up to date. | samjhana kc | 2017-03-21 11:24
6241 | Bug | Closed | Normal | When using search feature to find products. | Sapna Tuladhar | 2017-05-15 10:43
6223 | Bug | Closed | Normal | Logo couldn't be deleted as this logo has already been assigned to the product(placed order). | Sapna Tuladhar | 2017-03-20 13:00
6219 | Bug | Closed | High | Product detail page Crash Scenario | Sapna Tuladhar | 2017-03-21 11:43
6218 | Bug | Closed | Normal | Validation is required in Logo file upload. | Ashish Bastakoti | 2017-03-20 09:56
6208 | Bug | Closed | High | The product quantity and price issue in the Cart page | Ashish Bastakoti | 2017-03-20 10:27
6207 | Bug | Closed | Normal | Some product's detail pages have been crashing. | Sapna Tuladhar | 2017-03-21 13:05
6206 | Bug | Closed | Normal | The correct number of products cannot be ordered from a grid view | Ashish Bastakoti | 2017-03-20 10:26
6204 | Bug | Closed | Normal | Prices can be in decimal form. | Sapna Tuladhar | 2017-03-20 12:52
6203 | Bug | Closed | Normal | If user tries to edit split order, error page is thrown. | Sapna Tuladhar | 2017-03-20 11:47
6199 | Bug | Fixed | High | Stores Module (Front-end "Shipping Page") : JS issue | Chris Lurty | 2017-03-21 11:03
6198 | Bug | Closed | High | Stores Module (Front-end "Product Detail Page") : the logos on modal image problem | Ashish Bastakoti | 2017-03-21 11:10
6196 | Bug | Closed | High | looks like the S3 permissions aren't set correctly | Ashish Bastakoti | 2017-03-20 10:26
6195 | Bug | Closed | High | Store Module (Back-end) : Admin cannot edit/delete logo in Logo tab from Store Edit | Ashish Bastakoti | 2017-03-20 09:48
6181 | Bug | Closed | High | Crash during order placement when no business address supplied | Saman Kapali | 2017-03-15 16:10
6178 | Bug | Closed | High | If the Order detail for a customer is edited, all the other details are also replaced | Ashish Bastakoti | 2017-03-23 12:41
6177 | Bug | Closed | High | The Customer and Shipping Info if changed, shouldn't be updated to the Login Information and default Shipping info for Customer | Ashish Bastakoti | 2017-03-23 12:41
6174 | Bug | Closed | Normal | If the admin privileges is switched On/Off, the contact number is deleted from the customer info | Ashish Bastakoti | 2017-03-20 09:28
6173 | Bug | Closed | Low | Button enabling issue in contact info | Saman Kapali | 2017-03-23 09:35
6170 | Bug | Closed | Normal | User can add products to cart more than that mentioned in stock | Ashish Bastakoti | 2017-03-21 11:26
6169 | Bug | Closed | Normal | For the stores with no default products but custom products, the product doesn't display if selected from menu but the products display randomly | Ashish Bastakoti | 2017-03-21 11:05
6168 | Task | Backlog | Normal | Updated Home Page | N/A | 2017-03-16 09:15
6162 | Bug | Backlog | High | If a certain product of specific size from a bulk is changed status in vendor-orders then the main orders are not displayed in any status's page. | Subin Shakya | 2017-03-14 16:52
6161 | Bug | Closed | Normal | Provide Validation to Customer Info and Shipping Info in Order Details page as well. | Ashish Bastakoti | 2017-03-23 12:33
6160 | Bug | Closed | Normal | Prices are left aligned on thumbnails of default products. | Sapna Tuladhar | 2017-03-16 09:39
6159 | Bug | Closed | Normal | The total price on the data table for Orders should be Net-Total, not sub-total | Ashish Bastakoti | 2017-03-20 09:27
6157 | Bug | Closed | Normal | Product quantity doesn't match with the total number of selected products on default_products page. | Sapna Tuladhar | 2017-03-20 12:59
6155 | Bug | Closed | High | If a company is created without any stores, and the company URL is accessed, the application crashes. | Ashish Bastakoti | 2017-03-21 11:09
6154 | Bug | Closed | Normal | Edit feature is not working for shipping address. | Sapna Tuladhar | 2017-03-16 11:39
6153 | Bug | Closed | Normal | Error while spliting order | Saman Kapali | 2017-03-15 13:39
6152 | Bug | Closed | Normal | While adding new address into shipping option section. | Sapna Tuladhar | 2017-03-21 13:43
6151 | Bug | Closed | Normal | Price and size match issue, while editing order. | Saman Kapali | 2017-03-15 16:50
6150 | Bug | Closed | Normal | Existing products are not displayed in default products section but is displayed on all products section in Stores module | Ashish Bastakoti | 2017-03-20 09:25
6139 | Bug | Closed | Normal | On clicking Replace button from Vendor-Order, Order Status is blanked and no orders displayed in Order Status's page. | Ashish Bastakoti | 2017-03-20 09:27
6136 | Bug | Closed | Normal | On clicking dkpk store, page crashes. | Sapna Tuladhar | 2017-03-16 10:19
6135 | Bug | Closed | Normal | Exception should be handled properly if user tries to open invalid url from back end. | Sapna Tuladhar | 2017-03-20 10:21
6130 | Bug | Closed | Normal | Products remain on cart after a order is placed successfully | Saman Kapali | 2017-03-15 16:51
6129 | Bug | Backlog | Normal | Provide Admin privileges to user and refresh the front end, doesnot display Logged In as Admin | samjhana kc | 2017-03-13 14:47
6128 | Bug | In Progress | High | The price do not match in Order Processing (BackEnd) | Subin Shakya | 2017-03-16 12:38
6127 | Bug | Closed | Normal | "Allow Shipping to Other Addresses" toggle switch couldn't be disabled. | Sapna Tuladhar | 2017-03-16 11:17
6126 | Bug | Backlog | Normal | The twilo validation is not working if the phone number is added from the back-end which was not validated properly there too. | samjhana kc | 2017-03-13 13:49
6125 | Bug | Closed | Normal | When trying to add new store from view company section. | Sapna Tuladhar | 2017-03-16 11:16
6124 | Bug | Closed | Normal | Though the Store is created from Company Edit, an error message is provided! | Ashish Bastakoti | 2017-03-20 09:25
6123 | Bug | Closed | Normal | Exception should be handled properly if user tried to place order twice. | Sapna Tuladhar | 2017-03-16 11:13
6120 | Bug | Closed | High | Crash during order placement | Saman Kapali | 2017-03-15 16:47
6119 | Bug | Closed | Normal | Price unit is only available for default items. | Sapna Tuladhar | 2017-03-16 11:11
6118 | Bug | Closed | Normal | Both the stores are considered default store and non of them can be deleted | Ashish Bastakoti | 2017-03-13 11:11
6117 | Bug | Closed | Normal | style id without having preview image is displaying on the drop down list when tried to add default items. | Sapna Tuladhar | 2017-03-16 11:01
6115 | Bug | Closed | Normal | Allow shipping to other addresses toggle switch should be auto active. | Sapna Tuladhar | 2017-03-16 10:50
6113 | Bug | Backlog | Normal | Shipping Info Page is not displayed instead a message is provided after valid details are entered from Contact Info Page | samjhana kc | 2017-03-10 14:39
6112 | Bug | Closed | Normal | Unable to delete a carted item on windows. | Sapna Tuladhar | 2017-03-20 10:19
6111 | Bug | Closed | Normal | Exception is thrown when tried to enter duplicate email address in customer page. | Sapna Tuladhar | 2017-03-14 15:54
6110 | Bug | Closed | Normal | The admin privileges if turned off cannot be switched on again | Ashish Bastakoti | 2017-03-13 11:35
6108 | Bug | Closed | High | Error while adding products | Saman Kapali | 2017-03-10 16:09
6105 | Bug | Backlog | Normal | Use same validation through out the application, the submit button is disabled even if required fields are entered. | Subin Shakya | 2017-03-20 10:18
6104 | Bug | Closed | Normal | hierarchy during adding categories | Lalit Thapa | 2017-03-10 16:08
6103 | Improvement | Closed | Normal | Indicator in adding products | Saman Kapali | 2017-03-10 16:56
6102 | Backlog | Closed | High | Can add two products from two categories | Saman Kapali | 2017-03-15 16:46
6100 | Bug | Closed | High | Cannot add two products with same name in same custom category and | Saman Kapali | 2017-03-10 16:48
6099 | Bug | Closed | Normal | When clicked on eye icon to view the image of carted item. | Sapna Tuladhar | 2017-03-16 10:43
6098 | Bug | Closed | High | Can edit billing without edit permission | Saman Kapali | 2017-03-14 09:10
6097 | Bug | Closed | Normal | When using search feature to find company/store. | Sapna Tuladhar | 2017-03-16 10:30
6095 | Bug | Closed | Normal | The buttons should be disabled in view mode | Ashish Bastakoti | 2017-03-13 11:21
6092 | Bug | Closed | High | The UI and js not working in Safari browser | Ashish Bastakoti | 2017-03-21 09:25
6091 | Bug | Closed | Normal | After the admin is created for a store the user is directed back to the Store edit mode but the admin is not listed! | Ashish Bastakoti | 2017-03-13 11:06
6090 | Bug | Closed | Normal | Stores - Stores (Create Company) : The detail tab should open by default | Ashish Bastakoti | 2017-03-13 11:32
6088 | Bug | Closed | Normal | Display a default message in every data table if there are no items | Ashish Bastakoti | 2017-03-20 09:24
6084 | Bug | Backlog | Normal | Slider is not working on front end. | samjhana kc | 2017-03-16 10:13
6080 | Bug | Closed | High | Error after a product is deleted from the order list. | Saman Kapali | 2017-03-10 14:45
6078 | Bug | Closed | High | Browser Specific bug | Saman Kapali | 2017-03-10 14:40
6077 | Bug | Closed | High | Zero total error | Saman Kapali | 2017-03-10 14:39
6076 | Bug | Closed | High | Page crash while order with amount greater than $999 | Saman Kapali | 2017-03-10 17:31
6072 | Bug | Closed | Normal | When moving cursor towards sign out option. | Sapna Tuladhar | 2017-03-13 15:01
6071 | Bug | Closed | Normal | When edited the item size, price of the item got resetted. | Sapna Tuladhar | 2017-03-13 15:01
6069 | Bug | Closed | Normal | When clicked on order now button, eception is thrown. | Sapna Tuladhar | 2017-03-16 09:42
6063 | Task | Closed | Normal | Admin order creating issue | Saman Kapali | 2017-03-14 09:10
6061 | Bug | Closed | High | Crash during order placement | Saman Kapali | 2017-03-10 14:46
6060 | Bug | Closed | High | User deletion not handled properly. | Saman Kapali | 2017-03-10 15:43
6051 | Task | Done | Normal | Changes in User - Backend (User Module) | Chris Lurty | 2017-03-13 11:40
6050 | Task | Done | Normal | Changes in Details tab - Backend (Store Module) | Chris Lurty | 2017-03-13 11:40
6049 | Task | Backlog | Normal | Changes in Company - Frontend (Stores Module) | samjhana kc | 2017-03-08 09:20
6048 | Task | Done | Normal | Changes in Company - Backend (Stores Module) | Chris Lurty | 2017-03-13 11:40
6039 | Task | Fixed | High | Id assignment of webelements. | Saman Kapali | 2017-03-07 15:54
6006 | Improvement | Backlog | Normal | Changes in the Store Cart - Frontend (Stores Module) | samjhana kc | 2017-02-27 13:30
6005 | Task | Backlog | Normal | Store HomePage - Frontend (Store Module) | samjhana kc | 2017-02-28 00:24
6003 | Task | Done | Normal | Changes in Products tab - Backend (Stores Modules) | Chris Lurty | 2017-02-27 15:48
6002 | Task | Backlog | Normal | Add Custom Filters in the Frontend | samjhana kc | 2017-02-27 13:13
6001 | Task | In Progress | Normal | Changes in Appearance - Backend (Stores Modules) | Subin Shakya | 2017-03-10 14:43
6000 | Task | Backlog | Normal | Changes in Shipping Option - Backend (Stores Module) | samjhana kc | 2017-03-10 14:56
5999 | Task | Backlog | Normal | Changes to the Billing System - Backend (Stores Module) | Subin Shakya | 2017-02-28 13:18
5986 | Bug | Done | High | The store products aren't updating | Chris Lurty | 2017-02-22 11:33
5985 | Improvement | Backlog | Normal | Store Menu Layout Design | samjhana kc | 2017-02-22 10:36
5982 | Task | Backlog | Normal | Messaging - Again | Lalit Thapa | 2017-02-21 02:47
5981 | Task | Backlog | Normal | Handle the Pricing in both back-end and Front-end using floats | Subin Shakya | 2017-02-20 16:39
5980 | Improvement | Fixed | Normal | Improvements in Order Table and Order items table | Chris Lurty | 2017-02-21 15:45
5979 | Improvement | Done | Normal | Improvement in Order Processing in Back-end | Chris Lurty | 2017-02-27 12:57
5978 | Improvement | Backlog | Normal | Improvement in Payment Info Page | samjhana kc | 2017-03-02 13:16
5977 | Improvement | In Progress | Normal | Improvement in Shipping Page | samjhana kc | 2017-02-22 00:28
5976 | Improvement | Backlog | Normal | Improvement in Contact Info Page | samjhana kc | 2017-03-02 13:23
5975 | Improvement | In Progress | Normal | Improvement in Cart Page | samjhana kc | 2017-02-21 23:45
5974 | Improvement | In Progress | Normal | Improvement for Logo Preview | samjhana kc | 2017-02-21 21:37
5973 | Bug | Done | Normal | The footer should have a minimum height so that it is always in the foot of the page. | Chris Lurty | 2017-02-21 18:03
5972 | Improvement | Done | Normal | View and Edit for the Stores and Company should be Carried out seperately. | Chris Lurty | 2017-02-20 17:28
5925 | Task | Backlog | Normal | Cart Page Update | samjhana kc | 2017-02-07 03:07
5907 | Task | Backlog | Normal | Order Confirmation Email | samjhana kc | 2017-02-03 00:26
5848 | Task | Done | Normal | Quick Fixes - Please fix ASAP! | Chris Lurty | 2017-02-22 10:49
5847 | Task | Backlog | Normal | Shipping | samjhana kc | 2017-01-26 00:45
5846 | Task | Backlog | Normal | Credit Card Processing | samjhana kc | 2017-01-24 21:58
5770 | Task | Done | Normal | Company page and Store page in Frontend | Chris Lurty | 2017-03-20 13:28
5767 | Task | Backlog | Normal | Please explain the use of cookies and Company Store addresses during checkout. | Chris Lurty | 2017-01-27 00:50
5766 | Task | Backlog | Normal | Please define the role of a Store Admin | Subin Shakya | 2017-01-12 20:38
5765 | Task | Backlog | Normal | Please explain 'Product Ordering Page' | Subin Shakya | 2017-02-03 00:10
5760 | Task | Done | High | Please specify the Product Import Method for Vendor Barco Uniforms and provide the details. | Chris Lurty | 2017-02-16 10:21
5759 | Task | Done | Normal | Please specify the Product Import Method for Vendor White Swan and provide the details. | Chris Lurty | 2017-02-10 09:30
5758 | Task | Done | Normal | Please specify the Product Import Method for Vendor Landau and provide the details. | Chris Lurty | 2017-02-07 10:56
5757 | Task | Done | Normal | Please specify the Product Import Method for Vendor Strategic Partners and provide the details. | Chris Lurty | 2017-02-07 10:56
5756 | Task | Done | Normal | Please specify the Product Import Method for Vendor AlphaBorder and provide the details. | Chris Lurty | 2017-02-07 10:55
5755 | Task | Done | Normal | Please specify the Product Import Method for Vendor SanMar and provide the details. | Chris Lurty | 2017-02-07 10:55
5597 | Bug | Closed | High | Admin login validation | Saman Kapali | 2016-12-30 13:02
5595 | Task | Backlog | Normal | Footer | samjhana kc | 2016-12-30 10:25
5510 | Task | Backlog | Normal | Inventory | Chris Lurty | 2016-12-30 16:57
5502 | Task | Backlog | Normal | title, url and search | samjhana kc | 2016-12-13 17:09
5343 | Task | In Progress | Normal | Users Section | Chris Lurty | 2016-11-28 16:06
5311 | Task | Closed | Urgent | Git File List | Chris Lurty | 2016-12-05 20:53
5307 | Bug | Closed | Urgent | Product Import Error | Chris Lurty | 2016-11-10 21:06
5292 | Task | Backlog | High | Store Logos | Subin Shakya | 2017-01-04 23:04
5291 | Task | Backlog | High | Product Pricing | samjhana kc | 2017-01-16 21:56
5290 | Task | Backlog | High | Database Access | Chris Lurty | 2016-11-14 12:15
5281 | Task | Backlog | Normal | Checkout Page | Jeetendra Maharjan | 2016-11-18 21:22
5263 | Task | In Progress | Normal | Shopping Cart | samjhana kc | 2016-11-09 03:44
5246 | Task | Backlog | Normal | Icons | samjhana kc | 2016-11-08 10:48
5236 | Task | Done | Normal | Store Logos | Chris Lurty | 2017-03-20 09:53
5235 | Task | Done | Normal | Companies | Chris Lurty | 2017-02-07 10:57
5234 | Task | In Progress | Normal | Updated Product Search Page | Chris Lurty | 2017-01-17 09:01
5233 | Task | In Progress | Normal | Use subdomains for assets | samjhana kc | 2016-11-15 00:24
5213 | Task | In Progress | Normal | Store Appearance | Chris Lurty | 2016-11-16 17:31
5212 | Task | In Progress | Normal | Product Detail Page | Chris Lurty | 2017-01-13 08:59
5195 | Task | Backlog | Normal | css and js file organization | samjhana kc | 2016-12-30 07:06
5180 | Task | Done | Urgent | Store Product List | Chris Lurty | 2017-02-07 17:32
5179 | Task | In Progress | Normal | Default Products Section | Chris Lurty | 2016-11-14 12:25
5178 | Backlog | Closed | Normal | Default products in store. | Chris Lurty | 2016-11-07 21:33
5164 | Task | Closed | Normal | Store form match format | Chris Lurty | 2016-11-07 21:32
5163 | Task | Closed | Low | switches missing in the store form | Chris Lurty | 2016-11-07 21:39
5162 | Task | Closed | Low | Reduce size of checkboxes and switches | Chris Lurty | 2016-11-07 21:36
5161 | Task | Closed | Low | Strategic Partners Import | Chris Lurty | 2016-11-08 00:56
5160 | Bug | Closed | High | Error when accessing product page | Chris Lurty | 2016-11-07 21:37
5149 | Support | In Progress | High | Message Module | Chris Lurty | 2016-11-22 17:40
5147 | Support | Backlog | High | Store Page Sidebar | samjhana kc | 2017-03-13 09:25
5146 | Support | Backlog | High | Sign In at frontend | samjhana kc | 2016-11-04 17:30
5142 | Task | Backlog | High | Regarding Campaign | Chris Lurty | 2016-10-25 21:22